BOND Guidance Notes Series 1

Beginner's Guide to Logical Framework Analysis

Top Tips

What is a Logical Framework?

A log frame (also known as a Project Framework) is a planning tool for development projects. It looks like a table (or framework) and aims both to be logical to complete, and to present information about projects in a concise, logical and systematic way. The log frame model was developed in the United States and has since been adopted and developed by many other donors, including the Department For International Development (DFID). A log frame summarises, in a standard format:

- what your project is trying to achieve

- how it aims to do this

- what is needed to ensure success

- ways of measuring progress

- and the potential problems along the way.

Why use Logical Framework Analysis?

Because 9 out of 10 donors prefer it...? Donors aside, LFA can be a useful tool, both in the planning and the monitoring of development projects. It is not the only planning tool, and should not be considered an end in itself, but offers a useful process of thinking by imposing the discipline of being clear and specific about what you're trying to do and how, and highlighting what success depends on. The log frame also provides a handy summary to inform project staff, donors, beneficiaries and other stakeholders, which can be referred to (and adapted) throughout the project's lifecycle, to systematically identify obstacles and changes to aims and outputs.

So, what is so intimidating about using a logical framework? Perhaps because we are very conscious of the complexity of development projects, we find it hard to believe that they can be reduced to one side of A4 (why not use A3, or A2 instead)? Remember that the log frame isn't intended to show every detail of your project, nor to limit your project to what can be shown on one page. It is simply a convenient overview of the key factors.

Who should be involved?

The reality of funding proposals and completing log frames usually means a desk officer in the UK trying to summarise a project outline for a funding application. However, if used correctly as a planning tool, the log frame ought to be developed by the person most closely involved in project implementation. This will most likely be your project co-ordinator or partner organisation overseas.

Writing log frames in the UK is not participatory, and this has led to criticism of log frames as a planning tool. It is more useful to think of the log frame as a process of thinking and during the planning stage you can use participatory approaches to feed into the log frame process. Whilst project beneficiaries may not identify easily with the concept of a logical framework, they may be able to identify the factors that are critical to project success, as well as the most appropriate measures (indicators) of progress. In this way, participatory techniques can be used to inform the logical framework. The log frame can also provide a guide as to what information needs to be gathered through participatory processes, and can be used to synthesise the outcomes of other planning tools, such as social mapping, wealth ranking, and problem and objective trees.

If the log frame is written, adapted or changed in the UK, it is important to feed it back to fieldworkers and partners (and other relevant stakeholders) overseas. The input to a log frame should be a team effort, as much as possible. If you are not the person closest to the project, try and engage that person in developing the log frame. Always consider what impact the objectives & indicators will have on their work what is realistically achievable? Will they have enough time to collect the information you are asking for? What assumptions are you making unconsciously that might be obvious to them?

What does all the jargon mean?

Some of the terminology attached to log frames is familiar, though it may seem rather intimidating. Log frames were first developed by the US military, and some of the jargon has stuck. Don't be put off by the language. Remember that your goal, purpose, outputs and activities are all objectives (at different levels of the project hierarchy). There are several different models of log frames, and you may come across some or all of the following terms:

| TERM | MEANING | EXAMPLE |
| --- | --- | --- |
| Goal | the ultimate result to which your project is contributing | Jamaica's dominance of competitive bob-sledding |
| Purpose | the specific aim / objective of your project | Jamaica wins the gold medal for bob-sledding at the 2002 Winter Olympics |
| Outputs | the work (targets) needed to be done in order to achieve this | Team members selected by (date)... Team at full fitness by (date)... etc. |
| Activities | the actual tasks required to produce the desired outputs | Develop training schedule... Find practice venue... Publicity campaign to recruit team members... etc. |
| Inputs | what resources (materials) are needed to carry out the tasks | Funding... Coach... Bob-sled... Snow... Medical advisor... etc. |
| Indicators | also referred to as measurable or objectively verifiable indicators (O.V.I) - ways of measuring progress towards the achievement of the goal i.e. the targets or standards to be met at each stage | 1. Team members capable of running x metres in x seconds by x time... 2. 4 year training schedule, budget and outcomes developed & agreed by x... etc. |
| Means of verification | (M.O.V.) are methods for collecting the information (data) required to assess progress against indicators | 1. Fitness report from team doctor 2. Schedule written & agreed (signed) by coach, team members & team doctor |
| Assumptions | the external factors (challenges / threats) which are likely to influence (jeopardise) your work at each stage | The Jamaican team qualifies for the Games... it snows enough for the Games to be held...etc. |
| Supergoal | the long-term results of continued achievement of your goal | Hot countries seen as serious competitors in winter sports |

What inputs (materials) do I need?

- Blank log frame (see examples Figures. 1 & 2)

- Pencil & eraser so you can adjust and amend as you go along

- Somewhere to work (and think) without distractions

- As much information about the planned project as possible - preferably do it 'on site' and you also need to be good at KISSing … … Keep It Simple, Stupid!

Now, where do I start?h

The key to completing log frames is to:

- start at the top and work down the objectives column (what do you want to do?)

- then think laterally (how can you measure your progress against objectives?)

- then reflect back up (what assumptions are you making and what are their implications?)

If you wish, you can identify the indicators, means of verification and assumptions for each objective / output / activity as you go along, but you may get bogged down in the detail before the project has taken shape. You should find it easier to complete the objectives column first and then return to look at the indicators afterwards.

Figure 1: A Logical Framework (DFID model) 
Taken from DFID's "Guidelines on Humanitarian Assistance", May 1997

| Objectives | Measurable Indicators | Means of Verification | Important Assumptions |
| --- | --- | --- | --- |
| Goal Wider problem the project will help to resolve | Quantitative ways of measuring or qualitative ways of judging timed achievement of goal | Cost-effective methods and sources to quantify or assess indicators | Goal to Supergoal External factors necessary to sustain objectives in the long run |
| Purpose The immediate impact on the project area or target group i.e. the change or benefit to be achieved by the project | Quantitative ways of measuring or qualitative ways of judging timed achievement of purpose | Cost-effective methods and sources to quantify or assess indicators | Purpose to Goal External conditions necessary if achieved project purpose is to contribute to reaching project goal |
| Outputs These are specifically deliverable results expected from the project to attain the purpose | Quantitative ways of measuring or qualitative ways of judging timed achievement of outputs | Cost-effective methods and sources to quantify or assess indicators | Outputs to Purpose Factors out of project control which, if present, could restrict progress from outputs to achieving project purpose |
| Activities These are the tasks to be done to produce the outputs | Inputs This is a summary of the project budget | Financial report as agreed in grant agreement | Activity to Output Factors out of project control which, if present, could restrict progress from activities to achieving outputs |

DFID describes the Logical Framework as "a tool to help designers of projects think logically (hence the name) about what the project is trying to achieve (the purpose), what things the project needs to do to bring that about (the outputs) and what needs to be done to produce these outputs (the activities). The purpose of the project from the DFID viewpoint is to serve our higher level objectives (the goal)".

Stage One - Top Down (Objectives)

| 1 | Starting at the top, consider the overall GOAL of the project. What issue or problem is the project trying to address? The goal will be slightly beyond the reach of the project - what ultimate objective is the project contributing to? This should be a brief statement or summary. | E.g. to increase literacy among young people in the sub-Sahel region. TIP: try developing a problem tree, then turn the problems into objectives (this should help to determine at which level each objective fits into the hierarchy). |
| --- | --- | --- |
| 2 | What is the actual PURPOSE of the project? What final result are you trying to achieve? This should be brief and SMART: Specific Measurable Achievable Realistic Time-bound | For example "To increase literacy" is not a SMART objective, whereas "To increase school attendance of 6-14 year olds in (named region) of the sub-Sahel by 200% within 4 years" or "90% of all 6-14 years olds in (named region) of the sub-Sahel to have gained (particular level) of literacy skills within 4 years" are SMARTer (assuming they are realistic & achievable objectives!). |
| 3 | What are the particular OUTPUTS needed to achieve your purpose? There may be several outputs. These should be 'SMART' and it should also be clear how the achievement of outputs will lead to the fulfilment of the objective. | E.g. "Five new language teachers recruited and trained by (date)" and "Classes running in all schools at times when children are not required to complete family duties by (date)" and "Information sessions for families with school-age children held in each village demonstrating benefits of literacy by (date)" |
| 4 | What ACTIVITIES are needed to achieve these outputs? There may be several for each output, and statements should be brief (and SMART where appropriate) with an emphasis on action words. | For example, "Hold publicity campaign in (named region) to recruit language teachers by (date)" and "Agree and arrange selection process (& schedule) for teacher recruitment involving existing teaching staff by (date)" and "Hold training sessions for new teachers covering aims, approach, customs, potential problems holding information sessions, record-keeping, expenses, by (date) etc." and "Arrange appropriate accommodation for teachers in each village at least (? weeks) before arrival" etc. |
| 5 | What INPUTS are needed to carry out these activities? Again, there may be several for each activity, and it will help to run through each individually, listing required inputs (resources, equipment, tools, people). You can them group inputs and list each once rather than repeatedly. This will include a summary of the project budget (which should be attached to the log frame). | Budget (i.e. money!) Training space Accommodation Support of existing teaching staff Teaching materials Transport to village Project Co-ordinator / Fieldworker (who will be involved in all activities, but only needs to be listed once) etc. |

Stage Two - Work Across 
(Indicators & Verification)

As you work down each step of your objectives, think about how your outputs and activities can be measured. What indicators can be used to measure achievement against? What information will you need, and how can it be gathered? What problems, obstacles, barriers might arise to prevent the project from progressing as planned? How can their impact be minimised?

| 6 | Starting either from the top or the bottom of your hierarchy of objectives, begin to work across the log frame, identifying the INDICATORS for measuring your progress. Indicators need to define 'QQT' Quality - the kind (or nature) of the change Quantity - the scope (extent) of the change i.e. by how much, how many Timing - by when the change should have taken place There are two kinds of indicators you will need to use: |
| --- | --- |
|  | Process indicators | which measure the extent to which you have achieved your stated objectives | e.g. how many children attending school by (specified) time |
|  | Impact indicators | which help to monitor the achievement and the impact of your work | e.g. how many children pass (specified) literacy test at (specified) time |
|  | In addition, indicators can also be: |
|  | Direct Indirect (also known as soft or proxy) | e.g. the number of children attending school e.g. more books borrowed from the school library (suggesting more children reading, therefore wider literacy) |
|  | If you are confused about indicators - don't panic! Identifying indicators requires practice. Try to find a mentor with more experience. Or move on to look at means of verification - thinking about what information you need, and how to get it, may help to define what the indicator should be. If you come up with a long list of possible indicators try to narrow it down to the essential ones. |
| 7 | Next, try and work out your means of verification for each indicator. What information will you need, and how can it be gathered? Who will do this? Is this realistic - will they have the time and resources? Will they need to keep records, or can they get the information from somewhere else? Consider the cost implications and build this into the project budget. What management decisions may have to be made relating to monitoring activities? Don't exclude anecdotal evidence (e.g. views expressed by project beneficiaries, etc) if this is the most appropriate source of information, but remember that donors can be wary of this evidence, and you may later need to demonstrate your claims! |

Stage Three - Bottom Up (Assumptions)

| 8 | What external factors (outside your control) could affect the success of your project or prevent work from progressing? These may be climatic, political, economic, etc. but should be real (possible) risks rather than a list of everything that could go wrong, and should indicate how they might affect the work. Reflecting up from the bottom of your log frame, consider how each assumption affects the next stage of your project. | e.g. "sufficient rains to ensure that children are not required to replant crops and therefore unable to attend school" or "enough teachers with knowledge of local dialect (if not, may need wider recruitment and/or additional training)" or "conflict from neighbouring region doesn't spread into local area so that emergency needs take precedence over education". |
| --- | --- | --- |
| 9 | When you have completed your log frame, go back over it, from bottom to top, to check the 'logic' of it: Will the inputs and activities clearly lead to the outputs and purpose and contribute to the goal? Will your indicators and means of verification effectively measure your progress? Are your assumptions reasonable and avoidable, or are they so much of a risk that your project is unlikely to get off the ground or be completed? Are your project staff committed to the objectives and indicators identified? Are they realistic and achievable? Are there any changes you could make which will make it more workable? |
| 10 | When you have checked (and rechecked) your log frame and are satisfied that it is truly SMART, logical, and representative of your project, you can then type (or write) it up onto that A4 sheet - with a nice small font so that it all fits on the page - but is still large enough to read without a magnifying glass! At this point you should ensure that all the relevant stakeholders have had a chance to contribute to (and agree) it, before attaching it to your funding application and stick it on top of your project file, etc. But you haven't finished with it yet... remember that the log frame is a flexible tool for both planning and monitoring your project. As the project progresses and situations change, return to your log frame and revise it accordingly. This way, you will be able to follow through the assumptions again, and systematically identify any necessary changes to your objectives and indicators. Pass on these changes to your donors and other stakeholders, so that everyone can keep up to date with current progress. |

Top Tips

- Don't leave it to the last minute. Start working on your log frame when you begin planning the project. You may need to gather information as you go along that will be difficult to get later (e.g. baseline data against which to measure progress).

- Try and get the person planning and implementing the project to complete the log frame - if this is not possible, consider the implications of the objectives, indicators & verification on field staff and partners.

- Develop a problem tree. By turning the problems into objectives, this should help clarify the goal, purpose, outputs and activities of your project.

- Find a mentor with experience of writing log frames who can offer you advice & assistance

- If you get stuck, don't panic - move on to the next stage and come back to the tricky bit later.

- Work in pencil so you can erase things and make amendments easily, and use a large sheet of paper with plenty of room for 'thinking' then reduce it down to A4 later.

- You don't have to (won't!) get it right first time - keep reflecting and revising until you are satisfied that the project is workable and the log frame is clearly logical!

- Use the log frame throughout the project lifecycle to track progress and adapt to changing situations. You can use the log frame to review assumptions and implications, and to keep donors and other stakeholders informed of significant changes.

Where can I find out more about log frames?

- "Toolkits: a practical guide to assessment, monitoring, review and evaluation" (Development Manual 5), Louisa Gosling & Mike Edwards, £6.95 Save The Children, 1995, pp. 178-192

- DFID's "Guidelines on Humanitarian Assistance" published in May 1997 includes guidance on preparing log frames, and is available from DFID. You can also access guidance on the DFID web-site, including: Appendix 5 'What is a project framework?' at www.dfid.gov.uk/public/working/jfsapp5_ content.html DFID / ESCOR guidance (in Adobe Acrobat, which you can download free from the internet) is at:
www.dfid.gov.uk/public/working/ pdf/escor_guide.pdf and the completed example referred to (Annex 2) is at: www.dfid.gov.uk/public/working/escor_strategy.html

Acknowledgements

There guidance notes are drawn from training on LFA conducted for BOND by:

- Laurence Taylor (formerly Tutor Development Studies at Selly Oak Colleges), 37 Yardley Wood Road, Moseley, Birmingham B13 9JA

- Neil Thin, Department of Social Anthropology, University of Edinburgh, Adam Ferguson Building, George Square, Edinburgh EH8 9LL

- John Sartain, Tamarind Associates, 3 Kirklington Road, Southwell, Nottinghamshire NG25 0AR

Disclaimer: BOND Guidance Notes aim to encourage good practice through practical advice, however, BOND cannot be held responsible for the outcome of any actions taken as a result of the information contained in the Guidance Notes series.